## Plan
|  | Estimate | 840 | Actual | 845 | 211.25
Task Name | Start Date | End Date | Duration(days) | Man-hour | Predecessors | Note | Resources | Status
Set up a project team | 2023-01-11 | 2023-01-13 | 2 | 8 |  | Team-building activity - dinner | Total team | Completed
Work environment preparation | 2023-01-13 | 2023-01-16 | 3 | 64 |  | GitHub structure,Ubuntu,Qt | Total team | Completed
Branching and merging strategy | 2023-01-16 | 2023-01-17 | 1 | 8 |  |  | Yujie,Kaiwen | Completed
Determine project goals and scope | 2023-01-12 | 2023-01-20 | 8 | 32 |  | Project Overview;Discuss 4 alternative designs | Total team | Completed
Collect relevant information | 2023-01-12 | 2023-01-30 | 18 | 64 |  |  | Total team | Completed
Key content and highlights of presentation | 2023-01-15 | 2023-01-20 | 5 | 32 |  |  | Total team | Completed
Idea presentation and slide polish | 2023-01-20 | 2023-01-25 | 5 | 32 |  | Presentation PPT | Total team | Completed
Define team responsibilities | 2023-01-26 | 2023-01-30 | 4 | 16 |  | Team role & responsibilities | Total team | Completed
Develop communication\project monitoring plan | 2023-01-30 | 2023-01-30 | 0 | 8 |  | Weekly project meetings , in the library on Tuesdays from 10:00 to 12:00 | Total team | Completed
Defining architecture design | 2023-01-31 | 2023-01-31 |  | 24 |  | Architecture diagram | Total team | Completed
Identify project tasks and phases | 2023-01-31 | 2023-02-10 | 10 | 28 |  | Project planning | Total team | Completed
Product specification writing | 2023-01-26 | 2023-02-05 | 10 | 32 |  | Product requirements document | Yang Liu,Kaiwen | Completed
Product specification validation | 2023-02-05 | 2023-02-05 | 0 | 16 |  |  | Total team | Completed
UI interface design | 2023-02-05 | 2023-02-10 | 5 | 16 |  | UI design document | Yang Liu | Completed
UI interface validation | 2023-02-10 | 2023-02-10 |  | 8 |  |  | Total team | Completed
Deep learning model training | 2023-01-20 | 2023-03-31 |  |  |  |  | Wenjia,Yujie
yolov3 training | 2023-01-20 | 2023-01-25 | 5 | 24 |  |  | Wenjia,Yujie | Completed
yolov3 transefer to Raspberry Pi(c++) | 2023-01-25 | 2023-02-07 | 13 | 16 |  |  | Wenjia | Completed
.pt to .weights | 2023-02-07 | 2023-02-15 | 8 | 20 |  | try many methods to do that but find the latest yolov3 file do not support that transfer .pt to.weights | Wenjia | Completed
raspberry Pi camera and GPS module test | 2023-02-15 | 2023-02-22 | 7 | 10 |  |  | Wenjia | Completed
yolov5 training | 2023-02-22 | 2023-03-01 | 7 | 26 |  |  | Wenjia,Yujie | In progress
yolov5 transefer to Raspberry Pi(C++) | 2023-03-01 | 2023-03-15 | 14 | 30 |  |  | Wenjia | Completed
YOLOv5_lite training | 2023-03-15 | 2023-03-21 | 6 | 26 |  |  | Wenjia,Yujie | Completed
yolov5_lite transefer to Raspberry Pi(C++) | 2023-03-21 | 2023-03-31 | 10 | 20 |  |  | Wenjia | Completed
C++ program
qml
main.qml | 2023-02-20 | 2023-03-01 | 9 | 4 |  |  | Kaiwen | Completed
ConfigView.qml | 2023-02-20 | 2023-03-01 | 9 | 4 |  |  | Kaiwen | Completed
CusTitleBar.qml | 2023-02-20 | 2023-03-03 | 11 | 4 |  |  | Kaiwen | Completed
CusToolBar.qml | 2023-02-20 | 2023-03-03 | 11 | 4 |  |  | Kaiwen | Completed
QT "Home" window design | 2023-02-20 | 2023-03-03 | 11 | 4 |  | HomeView.qml | Kaiwen | Completed
MainForm.qml | 2023-02-20 | 2023-03-03 | 11 | 4 |  |  | Kaiwen | Completed
QT "Result" window design | 2023-03-12 | 2023-03-29 | 17 | 4 |  | ResultView.qml；resultlistmodel；resultlistdata | Kaiwen | Completed
QT "Setting" window design | 2023-02-20 | 2023-03-03 | 11 | 6 |  | SettingView.qml | Kaiwen,Yujie | Completed
QT "Task" window design | 2023-02-20 | 2023-03-12 | 20 | 4 |  | TaskListView.qml；tasklistdata；tasklistmodel | Kaiwen | Completed
C++ code
UML diagram | 2023-03-12 | 2023-03-19 | 7 | 8 |  |  | Kaiwen,Yujie | Completed
CMakeLists.txt | 2023-03-12 | 2023-03-19 | 7 | 14 |  |  | Kaiwen | Completed
main | 2023-03-09 | 2023-03-12 | 3 | 4 |  |  | Kaiwen | Completed
monitor | 2023-03-12 | 2023-04-12 | 31 | 22 |  |  | Kaiwen | Completed
qpaintitem | 2023-03-12 | 2023-04-03 | 22 | 16 |  |  | Kaiwen | Completed
algorithm:cusncnn | 2023-03-31 | 2023-03-31 | 0 | 4 |  | cusncnn.h | Kaiwen | Completed
Camera driver design | 2023-03-12 | 2023-03-14 | 2 | 8 |  | camera.h;camera.cpp | Kaiwen | Completed
GNSS driver design | 2023-04-01 | 2023-04-04 | 3 | 8 |  | gtu7.h;gtu7.cpp | Kaiwen | Completed
serial driver design | 2023-04-01 | 2023-04-04 | 3 | 4 |  | serial.h;serial_linux.cpp;serial_win.cpp | Kaiwen | Completed
Combine code | 2023-03-05 | 2023-03-25 | 20 | 16 |  |  | Kaiwen | Completed
Deploy | 2023-04-15 | 2023-04-17 | 2 | 5 |  |  | Kaiwen | Completed
Release | 2023-04-17 | 2023-04-17 | 0 | 2 |  |  | Kaiwen | Completed
Weekly meeting | 2023-01-17 | 2023-04-11 | 84 | 84 |  |  | Total team | Completed
Post pictures, reels and videos on Insgram and Youtube | 2023-02-05 | 2023-04-03 | 15 | 10 |  |  | Yang Liu | Completed
Write process management and technical documentation | 2023-03-31 | 2023-04-17 | 15 | 32 |  |  | Total team | Completed
Configuration Management | 2023-01-13 | 2023-04-17 | 15 | 10 |  |  | Kaiwen | Completed