## Team (hidden)
Name | E-mail | Role |  | Mon.
Wenjia HAO | 2729835H@student.gla.ac.uk | Algorithms, data sets |  | Tud.
Kaiwen DONG | 2749039d@student.gla.ac.uk | Procurement and hardware |  | Wed.
Yang LIU | 2749545L@student.gla.ac.uk |  |  | Thu.
Yujie LIU | 2544989l@student.gla.ac.uk |  |  | Fri.
Sat.
Date | Time | Meeting | Period | Sun.
Each Wednesday | 15:00-17:00 | Lab meeting | -
Each Friday | 14:00-15:00 | Team meeting | 1h
|  |  |  | week 4 | 2023-02-01
|  |  |  | week 5 | 2023-02-08
|  |  |  | week 6 | 2023-02-15
|  |  |  | week 7 | 2023-02-22
|  |  |  | week 8 | 2023-03-01
|  |  |  | week 9 | 2023-03-08
|  |  |  | week 10 | 2023-03-15
|  |  |  | week 11 | 2023-03-22
|  |  |  | week 12 | 2023-03-29
|  |  |  | week 13 | 2023-04-05
|  |  |  | week 14 | 2023-04-12

## 项目计划
Week | State | End Time | Weekday | Tasks | Description | Who | Associated deliverables
week 1 | Closed | 2023-01-11 | Wed. | Project Launch
week 1 | Closed | 2023-01-12 | Thu. | Team members |  | Kaiwen, Wenjia, Yujie, Yang LIU
week 1 | Closed | 2023-01-12 | Thu. | current tasks and plans |  | Yujie LIU
week 1 | Closed | 2023-01-13 | Fri | Discuss 4 alternative designs |  | Kaiwen, Wenjia, Yujie, Yang LIU
week 1 | Closed | 2023-01-13 | Fri | GitHub structure | set up a Github team(https://github.com/KW-DONG/Realtime-Programming) | Kaiwen
week 1 | Closed | 2023-01-16 | Mon. | Work environment preparation | Ubuntu,Qt,GitHub Desktop | ALL
week 1 | Closed | 2023-01-17 | Tud. | Team research rating sheet; Determine the scheme
week 2 | Closed | 2023-01-18 | Wed. | Scheme Design 3 and scheme Review | The third scheme, 3 choose 1 (according to the budget and score, achievable, time cycle to determine the scheme)
week 2 | Closed | 2023-01-20 | Fri. | Key content and highlights of the speech;；Team meeting | 14:00-15:00 | Kaiwen, Wenjia, Yujie, Yang LIU
| Closed | 2023-01-20 | Fri. | Moolde Teams |  | Kaiwen
week 2 | Closed | 2023-01-23 | Mon. | Responsible for PPT final draft |  | Yang LIU | PPT
week 3 | Open | 2023-01-25 | Wed. | Product vision, elevator speech，GIT (read me) | 5 minutes +2 slides; | Wenjia,Kaiwen
week 3 | Open | 2023-01-25 | Wed. | team building activity |  | Yujie
week 3 | Closed | 2023-01-30 | Mon. | background research | 带源码的论文，各2个 | Yujie, Yang LIU
week 3 | Open | 2023-01-30 | Mon. | 工作任务分解与指派 |  | Wenjia,Kaiwen
week 4 |  | 2023-02-01 |  |  | Requirements review (feasibility, priority, iteration) | Estimate -- update the plan
week 5 |  | 2023-02-08 |  |  | Architecture review
week 6 |  | 2023-02-15 |  |  | preliminary design review
week 7 |  | 2023-02-22 |  |  | detailed design review
week 8 |  | 2023-03-01 |  |  | Development + unit testing | pair programming
week 9 |  | 2023-03-08 |  |  | Code review (before branch merging), integration + integration testing
week 10 |  | 2023-03-15
week 11 |  | 2023-03-22
week 12 |  | 2023-03-29
week 13 |  | 2023-04-05
week 14 |  | 2023-04-12
|  | 2023-04-17 |  | project submission
|  | After Easter break |  | Demo day

## Plan
|  | 预计小时 | 840 | 实际小时 | 644 | 161
Task Name | Start Date | End Date | Duration(days) | Man-hour | Predecessors | Note | Resources | Status
|  |  |  | 小时 | 前置任务 |  | 资源 | 状态
Set up a project team | 2023-01-11 | 2023-01-13 | 2 | 8 |  | Team-building activity - dinner | Total team | Completed
Work environment preparation | 2023-01-13 | 2023-01-16 | 3 | 64 |  | GitHub structure,Ubuntu,Qt | Total team | Completed
Branching and merging strategy | 2023-01-16 | 2023-01-17 | 1 | 8 |  |  | Yujie,Kaiwen | Completed
Determine project goals and scope | 2023-01-12 | 2023-01-20 | 8 | 32 |  | Project Overview;Discuss 4 alternative designs | Total team | Completed
Collect relevant information | 2023-01-12 | 2023-01-30 | 18 | 64 |  |  | Total team | Completed
Key content and highlights of presentation | 2023-01-15 | 2023-01-20 | 5 | 32 |  |  | Total team | Completed
idea presentation and slide polish | 2023-01-20 | 2023-01-25 | 5 | 32 |  | Presentation PPT | Total team | Completed
Define team responsibilities | 2023-01-26 | 2023-01-30 | 4 | 16 |  | Team role & responsibilities | Total team | Completed
Develop communication\project monitoring plan | 2023-01-30 | 2023-01-30 | 0 | 8 |  | Weekly project meetings , in the library on Tuesdays from 10:00 to 12:00 | Total team | Completed
Defining architecture design | 2023-01-31 | 2023-01-31 |  | 24 |  | Architecture diagram | Total team | Completed
Identify project tasks and phases | 2023-01-31 | 2023-02-10 | 10 | 28 |  | Project planning | Total team | Completed
Product specification writing | 2023-01-26 | 2023-02-05 | 10 | 32 |  | Product requirements document | Yang Liu,Kaiwen | Completed
Product specification validation | 2023-02-05 | 2023-02-05 | 0 | 16 |  |  | Total team | Completed
UI interface design | 2023-02-05 | 2023-02-10 | 5 | 16 |  | UI design document | Yang Liu | Completed
UI interface validation | 2023-02-10 | 2023-02-10 |  | 8 |  |  | Total team | Completed
Deep learning model training | 2023-01-20 | 2023-03-31 |  |  |  |  | Wenjia
yolov3 training | 2023-01-20 | 2023-01-25 | 5 | 24 |  |  | Wenjia,Yujie | Completed
yolov3 transefer to Raspberry Pi(c++) | 2023-01-25 | 2023-02-07 | 13 | 16 |  |  | Wenjia | Completed
.pt to .weights | 2023-02-07 | 2023-02-15 | 8 | 20 |  | try many methods to do that but find the latest yolov3 file do not support that transfer .pt to.weights | Wenjia | Completed
raspberry Pi camera and GPS module test | 2023-02-15 | 2023-02-22 | 7 | 10 |  |  | Wenjia | Completed
yolov5 training | 2023-02-22 | 2023-03-01 | 7 | 26 |  |  | Wenjia,Yujie | Completed
yolov5 transefer to Raspberry Pi(C++) | 2023-03-01 | 2023-03-15 | 14 | 30 |  |  | Wenjia | Completed
YOLOv5_lite training | 2023-03-15 | 2023-03-21 | 6 | 26 |  |  | Wenjia,Yujie | Completed
yolov5_lite transefer to Raspberry Pi(C++) | 2023-03-21 | 2023-03-31 | 10 | 20 |  |  | Wenjia | Completed
Weekly meeting | 2023-01-17 | 2023-04-11 | 84 | 84 |  |  | Total team | Completed
UML diagram,
Prepare process management and technical documentation | 2023-03-31 | 2023-04-17

## test case table
Test Case ID | Test Case Title | Preconditions | Test Steps | Expected Results | Actual Results | Test Result
TC001 | Test User Login Function | 1. Test application installed<br>2. User registered and has login credentials | 1. Open test application<br>2. Click "Login" button<br>3. Enter username and password<br>4. Click "Login" button | 1. User successfully logged in and entered application homepage<br>2. User's personal information and other functional modules displayed on homepage | User successfully logged in and entered application homepage, with personal information and functional modules displayed | Pass
TC002
TC003
TC004
TC005
TC006
TC007
TC008
TC009
TC010
TC011
TC012
TC013
TC014
TC015
TC016
TC017
TC018
TC019
TC020
TC021
TC022
TC023
TC024
TC025
TC026
TC027
TC028
TC029
TC030
TC031
TC032
TC033
TC034
TC035
TC036
TC037
TC038
TC039
TC040
TC041
TC042
TC043
TC044
TC045
TC046
TC047
TC048
TC049
TC050
TC051
TC052
TC053
TC054
TC055
TC056
TC057
TC058
TC059
TC060
TC061
TC062
TC063
TC064
TC065
TC066
TC067
TC068
TC069
TC070
TC071
TC072
TC073
TC074
TC075
TC076
TC077
TC078
TC079
TC080
TC081
TC082
TC083
TC084
TC085
TC086
TC087
TC088
TC089
TC090
TC091
TC092
TC093
TC094
TC095
TC096
TC097
TC098
TC099
TC100
TC101
TC102
TC103
TC104
TC105
TC106
TC107
TC108
TC109
TC110
TC111
TC112
TC113
TC114
TC115
TC116

## Meetings
[6 empty] | Open | Closed
Date | Questions and Discussion Points | Members | Tasks | Responsible Person | Planed Date | State
2023-01-17 | 10:00-11:00 方案选择及亮点讨论，演讲准备 | 4 | 完成：Work environment preparation Branching and merging strategy 准备：Product vision, elevator speech，GIT (read me) | ALL | 2023-01-23 | Closed
2023-01-23 | 10:00-11:00 演讲终稿演练 | 4 | Collect relevant information：本周开始每人找带源码的论文，各2个； Key content and highlights of presentation idea presentation and slide polish | Yujie, Yang LIU | 31/1/2023 | Closed
2023-01-31 | 10:00-11:00 实时显示，算帧数，支持读取本地照片; 参数：预制预处理 | 4 | 完成：Define team responsibilities Develop communication\project monitoring plan Defining architecture design | Yujie, Yang | 2023-02-07 | Closed
|  |  | 整理kaiwen架构流程图； 文档内容学习:Realtime embedded coding in C++ under Linux | Yujie, Yang |  | Open
|  |  | 代码链接:https://github.com/berndporr/opencv-camera-callback | Yujie, Yang |  | Open
|  |  | 安装:OPEN CV | Yujie, Yang |  | Open
|  |  | 学:1.callback;2.stdthread;每个驱动都是一根线程 | Yujie, Yang |  | Open
|  |  | 做:class camera,,读照片；uART 线程 | Yujie, Yang |  | Open
|  |  | 跑通：树莓派 C++； 物体检测 1-2 | Wenjia | 2023-02-07 | Closed
|  |  | 调模型,打包成一个函数 | Wenjia |  | Open
|  |  | 先做界面，2/7之前,(下一步调试界面--带相机去采图片) | Kaiwen | 2023-02-07 | Closed
|  |  | C++看驱动，openCV相机（moodle） | Yujie, Yang |  | Open
2023-02-07 | 10:00-11:00 1、讨论显示界面 |  | 按照kaiwen 所画草图，再次整理Axure样式表； kaiwen按照yang样式的QT编码 | Kaiwen, Yang | 2023-02-14 | Open
|  |  | Ins宣传： 1、界面展示 2、采购到位，硬件介绍 3、wenjia:模型迁移 | Yang | 2023-02-14 | Open
|  |  | 调YOLO V3 的pytorch 转darknet(失败，换V5) | Wenjia,Yujie | 2023-02-14 | Open
|  |  | 上传各自产出到HUB | all | 2023-02-14 | Open
|  |  | Issue更新 | all | 2023-02-14 | Open
2023-02-14 | 10:00-11:00 |  | 图片标注缺陷类别（最好找到新的类别）（后续可爬虫搜图片）
程序处理流程图；源代码及网页链接参考https://blog.csdn.net/weixin_44966641/article/details/122263759?ops_request_misc=%257B%2522request%255Fid%2522%253A%2522167509343916800192211003%2522%252C%2522scm%2522%253A%252220140713.130102334.pc%255Fall.%2522%257D&request_id=167509343916800192211003&biz_id=0&utm_medium=distribute.pc_search_result.none-task-blog-2~all~first_rank_ecpm_v1~rank_v31_ecpm-1-122263759-null-null.142%5Ev71%5Epc_search_v2,201%5Ev4%5Eadd_ask&utm_term=%E6%A0%91%E8%8E%93%E6%B4%BE%20%E6%91%84%E5%83%8F%E5%A4%B4%20c%2B%2B%20%E7%89%A9%E4%BD%93%E6%A3%80%E6%B5%8B&spm=1018.2226.3001.4187
|  |  | kaiwen按照yang样式的QT编码 | Kaiwen | 2023-02-14
|  |  | 配置文件，显示结果 | Kaiwen
|  |  | QT美化 | yuije
GPS
|  |  | YOLO V3-->YOLO V5 | Wenjia
|  |  | 树莓派官方相机，周五之前发邮件给老师 | Kaiwen | 2023-02-20 | Closed
2023-02-21 | 10:30 |  | 驱动：驱动摄像头，驱动GPS
界面
视觉物理检测
2023-02-28 | 11:00 |  | INS
2023-03-07 | 生病取消
2023-03-14 | YULO 5 的问题
2023-03-21 | 生病取消
2023-03-28 |  |  | 分支合并策略--readme | kaiwen
|  |  | 项目计划 | kaiwen、wenjia,yujie
|  |  | UI prd | liuyang
|  |  | YOLO V5 \YOLO V5 lite 操作过程 | wenjia | 测试报告：测试步骤、测试结果截图
|  | 实时性继续调试 | 树莓派1 及电脑性能测试 | wenjia
|  |  | 树莓派4B 及电脑性能测试 | wenjia
BUG及修复结果
|  |  | 程序设计（UML图）、结构、架构 | kaiwen\liuyang
|  |  | cmake 编译流程、 | kaiwen
|  |  | 硬件文档：GPS文档、相机、树莓派 | kaiwen
|  |  | 测试文档 | yujie

## Sheet2
Date: January 17th, 2023 Time: 10:00-11:00 Attendees: Total Team Agenda: Product vision Elevator speech GIT (read me) Discussion on plan selection and highlighting features Preparation for the presentation Proceedings: The meeting started with a discussion on the product vision, which was followed by a brainstorming session on the elevator speech. The team members shared their ideas and suggestions, and it was decided to finalize the speech in the next meeting. The discussion then moved on to GIT (read me) and the team was briefed on the importance of maintaining a clear and concise read me file for the project. It was decided that each team member would contribute to updating the read me file and ensure that it is up-to-date with the latest project changes. Next, the team reviewed the plan selection and highlighted features that would be discussed in the upcoming presentation. The team discussed the pros and cons of each plan and decided on the one that would best serve the product vision. Lastly, the team members discussed the preparation for the presentation and assigned tasks to each other. It was decided that a mock presentation would be conducted to ensure that all team members were well-prepared. Action Items: Finalize elevator speech in the next meeting Each team member to update the GIT read me file Conduct a mock presentation for preparation Conclusion: The meeting was productive, and the team made significant progress in the plan selection and highlighting features. The team members were enthusiastic and motivated to prepare for the upcoming presentation. The next meeting was scheduled, and all members were asked to come prepared with their assigned tasks.

## Questions List
Serial Number | Date | Questioner | Question Description | State |  | Open | Closed | Pengding
1 |  |  | QT是否能用 | Open
2 |  |  | 采购报销 | Open
3
4
5
6
7
8
9
|  |  | 分支合并策略--readme | kaiwen
|  |  | 项目计划 | kaiwen、wenjia,yujie
|  |  | UI prd | liuyang
|  |  | YOLO V5 \YOLO V5 lite 操作过程 | wenjia | 测试报告：测试步骤、测试结果截图
|  | 实时性继续调试 | 树莓派1 及电脑性能测试 | wenjia
|  |  | 树莓派4B 及电脑性能测试 | wenjia
BUG及修复结果
|  |  | 程序设计（UML图）、结构、架构 | kaiwen\liuyang
|  |  | cmake 编译流程、 | kaiwen
|  |  | 硬件文档：GPS文档、相机、树莓派 | kaiwen
|  |  | 测试文档 | yujie

## Purchasing List
Title | Type | Remarks(Chinese) | Cost | Link
Raspberry PI |  | 树莓派
camera |  | 摄像机 |  | https://www.amazon.co.uk/Dewanxin-Microphone-Streaming-Rotating-Conference/dp/B0891YNFQT/ref=sr_1_9?crid=44NDFINGX8ZT&keywords=webcam+1080p&qid=1675436969&sprefix=webcam+1080%2Caps%2C561&sr=8-9
breadboard |  | 面包板
GPS Module Receiver | Goouuu Tech GT-U7 |  | 13 GBP | https://www.amazon.co.uk/Navigation-Positioning-Microcontroller-Compatible-Sensitivity/dp/B08XGN4YLY/ref=sr_1_3?crid=2KXS44IICOL34&keywords=Quectel+gps&qid=1674314365&s=electronics&sprefix=quectel+gps%2Celectronics%2C72&sr=1-3

## Sheet1
win 有用，问助教

## Shared Links (hidden)
useful infor.
Serial Number | Topic | Links | Remarks(Chinese)
1 | Previous job demonstration | https://www.youtube.com/watch?v=wkhXxTbKkyo | 往年作业演示
2 | Mac Install the VM | https://blog.csdn.net/weixin_43667316/article/details/126314734 | Mac安装虚拟机
3 | Mac Dual system installation | https://blog.csdn.net/LBSGKD/article/details/122681929 | Mac安装双系统
4 | Ubuntu | https://releases.ubuntu.com/focal/ | Ubuntu版本
5 | Qt | https://download.qt.io/archive/qt/5.12/5.12.12/qt-opensource-linux-x64-5.12.12.run | Qt版本
6 | Previous operations | Release Signapse Helen Keller · albanjoseph/Signapse (github.com) | 往年作业
7 | github_reference1 | https://github.com/Nishant-web/oneTouchCozyMood | 指纹传感器按下放音乐和改变灯光
8 | github_reference2 | au6155/ComplicatedBikeLock: Project for the Real Time Embedded Programming course in university (github.com) | 面部识别，RFID身份验证和键盘的智能自行车锁
9 | github_reference3 | to9/PiSmartCenter: Home smart center based Raspberry Pi. (github.com) | QT 智能家居显示屏
10 | github_reference4 | Goddess-luo/Raspberry-PI-Smart-Home: 利用python语言进行编程设计，结合树莓派和小型电动机等硬件，通过软件的设计与硬件的相互协调，保证系统的正常运行。本文主要研究如何利用树莓派进行智能家居控制的程序设计，利用Python语言进行程序编写和其他的几个硬件设备完成自动窗帘的控制和温湿度的自动调控，并在自动模式之外可以进行手动的控制。进行本次研究，可以探寻树莓派在智能家居控制系统的设计方面的应用；同时通过与其他硬件搭配进行的设计，对探索不需要大幅度更改原有家居设备的情况下进行智能家居控制的方法有着重要意义。 (github.com) | 自动窗帘控制，温湿度调控但是用python
11 | github_reference5 | https://github.com/IcebergSam/Student-Residence-Assistant | 智能家居系统 QT c++
12 | Vehicle identification license plate recognition related
| Example 1 | https://blog.csdn.net/Zero___Chen/article/details/122020643?ops_request_misc=%257B%2522request%255Fid%2522%253A%2522167395580816800188582430%2522%252C%2522scm%2522%253A%252220140713.130102334..%2522%257D&request_id=167395580816800188582430&biz_id=0&utm_medium=distribute.pc_search_result.none-task-blog-2~all~baidu_landing_v2~default-1-122020643-null-null.142^v71^pc_search_v2,201^v4^add_ask&utm_term=%E8%BD%A6%E7%89%8C%E8%AF%86%E5%88%AB%20c%2B%2B&spm=1018.2226.3001.4187 | openCV C++ 车牌号识别
| Example 2 | EdjeElectronics (Evan) (github.com) | 行车记录仪树莓派
| Example 3 | AutoPi Telematics Unit CM4 ¦ AutoPi | 树莓派行车记录仪
13 | 带源码的论文
| An Iteratively Optimized Patch Label Inference Network for Automatic Pavement Distress Detection | https://ieeexplore-ieee-org.ezproxy.lib.gla.ac.uk/document/9447759 | 有代码和数据集
| A New Road Damage Detection Baseline with Attention Learning | https://www.mdpi.com/2076-3417/12/15/7594 | 有数据集
| Road defect detection from on-board cameras with scarce and cross-domain data | https://www.sciencedirect.com/science/article/pii/S0926580522004988 | 有部分参考代码
| Road Damage Detection and Classification Using Deep Neural Networks with Smartphone Images | https://onlinelibrary-wiley-com.ezproxy.lib.gla.ac.uk/doi/full/10.1111/mice.12387 | 有代码 jupyter notebook
| Transfer Learning-based Road Damage Detection for Multiple Countries | file:///Users/az/Downloads/Transfer_Learning-based_Road_Damage_Detection_for_.pdf | 有代码
| A bat-pigeon algorithm to crack detection-enabled autonomous vehicle navigation and mapping | https://reader.elsevier.com/reader/sd/pii/S2667305321000429?token=DDF1DA0CBC1F7AC205EBECE6A1A463B6BF948BDA888F4B8B05172D667B5D42C54EBF6E8EB22C07025DD576C2F18CA733&originRegion=eu-west-1&originCreation=20230124134045 | 无代码等，但内容很相关
| An annotated image dataset for automatic road damage detection using deep learning | https://reader.elsevier.com/reader/sd/pii/S2352340921004170?token=E58346A47A092E48EA0887943C955533F504CFF0B597344BF8B729424836D10540F770D6F766DF986B4D9B5B3F76314E&originRegion=eu-west-1&originCreation=20230124134329 | 有数据集
| c++ | https://www.bilibili.com/video/BV1dE41167hJ/?buvid=XU3AF763127C03954AD330FB781FCB7B52A45&is_story_h5=false&mid=vq%2F7%2FXTlteht2m1G0fVMGA%3D%3D&p=1&plat_id=116&share_from=ugc&share_medium=android&share_plat=android&share_session_id=2d24b5d8-1932-4f8d-8bba-a930df133095&share_source=WEIXIN&share_tag=s_i&timestamp=1674692368&unique_k=ADvDRCQ&up_id=438612988
| c | 1.1计算机和编程语言 - 计算机的思维方式重复是计算机最擅长的(SHD)_哔哩哔哩_bilibili
| 树莓派 C++ 物体检测 1） | (60条消息) 树莓派摄像头 C++ OpenCV YoloV3 实现实时目标检测_Adenialzz的博客-CSDN博客_yolov3 c++
| 树莓派 C++ 物体检测 2） | https://github.com/Adenialzz/Hello-AIDeployment

## Requirement List (hidden)
User Requirement | Priority | Task

## Designs (hidden)
Limitations
| Detection Object | Detection Objective | Application Market | Prospect | Flow Chart Description | Realizability | Revaluation Description | 45 Pounds | 8h*4*13=416 hours | 13 Weeks
序号 | 检测对象 | 检测目的 | 应用 | 市场前景 | 流程图说明 | 可实现性 | 评价说明 | Money(Pounds) | Time(Hours) | Implementation Period(Weeks)
1 | 零件 | 检测零件外观 | 工业相机；输出：好/不好；边缘检测，标记 |  |  | 实时要求不高，我们要做实时要求高的 | 放弃 |  |  |  | 0
序号: 3; 检测对象: 文本识别+语音; 检测目的: OCR验证证件真伪（黑白印刷字体识别）; 应用: 1、文本识别（文本扫描仪）； 2、识别后+语音朗读 |  |  |  | 0
4 | 人脸 | 人脸识别门锁 | 智能家居（物联网） |  |  | 去年已有人做过 | 放弃 |  |  |  | 0
5 | 车辆 | 智能行车记录仪+GPS | 行车记录仪： 1、车辆识别；（保底） 2、车牌识别；（保底） 3、GPS位置记录；（保底） 4、根据识别的车牌进行视频记录搜索； | 1.事故现场。根据模糊车牌信息、位置信息，查询定位视频。 2.刑侦/公安监控。 |  | 行车年度总结： 这一年您总共行驶了... 您与…陌生人擦肩而过 这一天您与牌号…的…车相遇了两次 您已点亮了这座城市…%的道路 …... |  |  |  |  | 0
6 | 智能识别 | 检测识别人体姿态 | 1.司机困意检测 2.物流，暴力分拣
7 | 智能识别 | 检测识别路面裂缝 | 相机+树莓派的模块； 智能行程记录仪，路面检测 |  |  | 可行。 硬件：相机+树莓派+GPS 软件：Python--c++
课结合方案，按需选择
序号 | 数据存储方式
1 | 本地数据文件
2 | 在线数据库
序号 | 输出方式
1 | 界面显示
2 | IO输出
3 | SPI总线

## Continuous_Assessment
|  | Proportion | Work | Assess What | Remarks(Chinese)
1 | Product vision | 10% | 1.initial pitch of the project (every team has 5 mins and two slides) ; 2.initial github pages up and running (special timeslot, see moodle). | the originality/usefulness of the work, if it has a solid realtime requirement and the quality of the presentation. | 10%的奖金将用于： 1.项目的初步介绍（每个团队有5分钟和两张幻灯片）； 2.初始github页面的建立和运行（特殊时段，见moodle）。 我们在此评估工作的原创性/实用性，是否有坚实的实时需求和演示的质量。
2 | the final submitted work | 25% | the way the code is structured | it is divided up in classes allowing encapsulation of data, 1.using data structures in a failsafe way, 2.receiving data and releasing data in a safe way 3.in general guaranteeing high reliability and ease of maintenance. | 最后提交的作品的25%的学分将基于代码的结构方式， 即它被划分为允许数据封装的类，以故障安全的方式使用数据结构，以安全的方式接收数据和释放数据，并在总体上保证高可靠性和易于维护。
3 |  | 25% |  | the realtime responsiveness of the software and how this has been achieved. This includes whether: 1.processing of events has been achieved by waking up threads 2. in general employing event driven code 3.using timers, signals, threads and/or kernel space interrupt driven coding in preference to polling or other less suitable methods. | 最后提交的作品的25%的学分将评估软件的实时响应性以及如何实现的。 这包括事件的处理是否通过唤醒线程来实现，以及一般采用事件驱动代码，使用定时器、信号、线程和/或内核空间中断驱动编码，而不是轮询或其他不太合适的方法。
4 |  | 25% | the use of revision control, committing, branching, creating releases, testing and project planning. | Marks will be awarded for : 1.demonstrating clear division of labour and documentation of the work. 2.Has git been used as a revision control system or just to ``upload'' code? 3.Has git been used to do revisions, track bugs 4.and has there been a release strategy? 5. Has the issue tracker system been used? 6.Have unit tests been used? | 最终提交的作品的25%的学分将基于修订控制、提交、分支、创建发布、测试和项目规划的使用。 如果能体现出明确的分工和工作记录，则可获得分数。 git是否被用作修订控制系统或只是用来"上载"代码？ git是否被用来做修订，跟踪bug，是否有一个发布策略？ 是否使用了问题跟踪器系统？是否使用了单元测试？
5 | promotion | 15% | the promotion of the work | 1.has the project been properly presented on github so that it catches the eye of a potential user? 2.Is the hard/software described in a way that other people can reproduce it? 3.Has the project been advertised on social media and has it been picked up by online publications such as hackaday? 4.Has a social media account been created and has it created a buzz around it? 5.Has the project a license? | 15%的分数用于作品的推广： 该项目是否在github上得到了适当的展示，从而吸引了潜在用户的目光？ 硬体/软件的描述方式是否能让其他人复制它？ 该项目是否在社交媒体上做了广告，是否被在线出版物（如hack aday）所采纳？ 是否已经创建了社交媒体账户，并在其周围创造了一个嗡嗡声 ？该项目是否有许可证？

## Continuous_Assessment_detail
2.Structure of the code | A1, A2 | A3, A4, A5 | B1, B2, B3 | C1, C2, C3 | D1, D2, D3 | E1, E2, E3 | F, G, H
| 22, 21 | 20–18 | 17–15 | 14–12 | 11–9 | 8–6 | 5–0(maybe CR)
Optimal choice of classes (SOLID) | Classes have clear responsibilies, interfaces are segregated to be client specific, dependency inversion, obey the Liskov Substitution Principle and documented in an intutive way. | Classes have clear responsibilies, interfaces are segregated to be client specific, dependency inversion, obey the Liskov Substitution Principle. Minor issues but still professional production standard. | Generally following the SOLID principles but either one is violated or documentation does not demonstrate that they have been taken into consideration. | Some SOLID principles haven’t been applied and/or there are violations of the principle. Documentation has flaws which makes it hard to see if/how they have been applied. | Serious flaws in the implementation of SOLID and most principles haven’t been applied. There is little mention in the documentation about the class choices. | Not clear whether SOLID has been applied or not. Some aspects appear to be applied but there is no direct evidence or documentation which makes it clear. | No application of SOLID or little to mark at all.
Encapsulation of data in classes and safe use of getters and setters and data management. | Clear public interfaces are defined, the data is private and getters and setters provide a safe interface to the client. Internal data structures are efficient and getters/setters provide fast acccess / compuation. | Public interfaces are defined, the data is private and getters and setters provide a safe interface to the client. However, some minor flaws for example in terms of safety, timing and choice of internal data structures. | Generally data is encapsulated and the internal storage of data is appropriate but there smaller issues with the getters / setters, not checking for fault conditions or the internal data storage could be more efficient. | Significant problems with encapsulation such as public variables and no fault checking. Data storage/management is inefficient. | Serious flaws in encapsulation with public variables being accessed, no clear getter/setter interfaces and data is stored in not appropriate structures. | No encapsulation in the classes used but classes work by accessing variables and calling member functions. No use of public / private variables & members. | No classes used, use of global variables or class-less coding.
Failsafe memory management | Memory management is completely leak free. | Memory management is leak free but uses new/delete where it could be avoided. | Excessive use of new/delete where C++ instances and copy constructors could be used. | Clearly there is a lack of care of tidying up memory allocations. | Serious flaws of memory management with eventual crash. | Serious flaws in memory management leading to out of memory. | No memory management at all or nothing to mark.
3. Realtime responsiveness | A1, A2 | A3, A4, A5 | B1, B2, B3 | C1, C2, C3 | D1, D2, D3 | E1, E2, E3 | F, G, H
| 22, 21 | 20–18 | 17–15 | 14–12 | 11–9 | 8–6 | 5–0(maybe CR)
Assessment of latencies in the application context and appropriate design decisions | Professional quantitative assessment and tolerances leading to clear coding decisions | Good quantitative assessment of the realtime demands leading to good coding decisions with small omissions. | Correct assessment of requirements but smaller shortcomings and resulting smaller issues in terms of coding decisions. | Assessment of the latencies partially wrong or not completely considered and the propose coding framework is not well thought through. | Latencies not seriously assessed and thus no justification of the realtime coding strategy. | Almost no effort to research in into latencies and their knock on effect on coding. | Achieved virtually nothing (consider CR)
Realtime coding | Production level realtime coding using threads/timers/signals and kernel interrupts | Perfectly working prototype but minor shortfalls in structure, doc or reliability. | Solid realtime coding but with smaller coding issues causing small noticeable latencies. | Realtime coding has shortcomings in responsiveness, timing and sampling of signals. | Significant shortcomings in the realtime coding resulting in long latencies. | Design shows major weaknesses in realtime processing utilising delays / blocking code.. | Showed few or none of the skills expected of a graduate (consider CR)
4. Revision control and project management | A1, A2 | A3, A4, A5 | B1, B2, B3 | C1, C2, C3 | D1, D2, D3 | E1, E2, E3 | F, G, H
| 22, 21 | 20–18 | 17–15 | 14–12 | 11–9 | 8–6 | 5–0(maybe CR)
Revision control | Professional use revision control with regular commits, branching & merging | Good use of revision control with detailed commits | Use of revision control but shortcomings in commits and development on master | Only work on master without any safeguards and shortcomings in commits | Only few commits on the master branch with generic comments. | Used github only as an upload site with no collaborative effort | Achieved virtually nothing (consider CR)
Project management | Exemplary; could not have done better with the time and resources available | High-quality planning, made excellent use of time and resources available | Good planning and use of resources with only minor deficiencies | Satisfactory planning but could clearly have made better use of resources. | Poor planning and use of resources; did not always follow directions | All over the place; required continual direction from supervisor | Did only what the supervisor told him or her, if tha
Reliability / Testing / Bug fixing | Professional testing approaches with unit tests, issue tracking, fixing | Good test scenarios which unit tests | Satisfactory testing and debugging but smaller shortcomings | Testing only in some cases but clearly some are left out. | Poor testing just in a qualitative manner, | No explicit testing but just report of success. | Achieved virtually nothing (consider CR)
5. Documentation and PR | A1, A2 | A3, A4, A5 | B1, B2, B3 | C1, C2, C3 | D1, D2, D3 | E1, E2, E3 | F, G, H
| 22, 21 | 20–18 | 17–15 | 14–12 | 11–9 | 8–6 | 5–0(maybe CR)
Quality of the content | Professional level of documentation comparable to other github prof projects | Comprehensive coverage with no significant omissions | Good coverage with only minor omissions | Covered much of the project but with significant omissions | Major omissions; large parts of project not covered | Only a little material relevant to project | Nothing of substance (consider CR)
Quality of argument | Could stay on github without further work | Arguments well presented; results clear and accessible | Results critically assessed | Discussion of results lacks insight | Discussion of results at only a very low level | Discussion perfunctory | No discussion apparent
Illustrations and video content | Worthy of publication | Well-chosen, illuminating and attractively formatted illustrations and excellent video | Good illustrations that enhance the report and an eye catching video | Illustrations satisfactory but could be drawn or chosen better; too few illustrations. Video could have clearer message. | Poor illustrations or mostly from WWW. Video film has low quality in terms of narrative and presentation. | Images only from WWW. The video has a poor quality. | No illustrations (consider CR)No video.
PR / social media strategy / release strategy | Perfectly devised strategy on all channels and targeting the right audience | Well devised strategy covering all relevant channels and target audience. | PR strategy reflects a good amateur project but has shortcomings for a prof product | PR OK for a local group of friends and followers but has shortcomings reaching beyond it | Poor PR just involving a few last minute posts on social media. No clear strategy. | PR strategy just limited to github. | No PR (consider CR)

## PPT框架 (hidden)
Page1
首页
Page2（General）
选择方案的评估标准： | Money(Pounds)，Time(Hours)，Implementation Period(Weeks)
采购item： | 摄像机,etc.
计划工时：
排期计划： | （甘特图等呈现）
Page3（详细介绍项目）
检测对象：
项目简介（/检测目的）：
数据存储方式：
输出方式：
方案评价标准：
应用场景：
应用场景：1.事故现场希望更快的查询模糊车牌信号或者gps地点更快找到视频记录
2.拓展到刑侦公安监控
智能行车记录仪
Page1
创新性、实用性
What/Why
原有的行车记录仪有什么gap ?比如发生事故或者需要证据需要一帧一帧的找不方便且耗时
赋能行车记录仪 通过查询模糊车牌信号或者gps地点更快找到视频记录
Page2
实时性、可行性
How
怎么去做 1.识别车牌 2.识别车辆车牌 3.实时gps通讯
应用场景：1.事故现场希望更快的查询模糊车牌信号或者gps地点更快找到视频记录 2.拓展到刑侦公安监控
软件图：树莓派；GPS、摄像头。 | 原创性、实时性、交付性
Page1
创新性、实用性
坑洞图片 drawbacks 智能行车记录仪：路面状况（车辆状况）、 创新：之前人工➡️路面病害探测road damage detector（树莓派+摄像头+GPS图片串联） 创新：之前只能检测行车检测➡️现在行车记录仪加上病态检测功能。提供接口。 产品/实用性：智能行车记录仪（带算法的行车记录仪） | 车牌识别系统。集成至行车记录仪，报告警察。 现有的行车记录仪只记录视频，赋能行车记录仪，增加功能：识别车牌，对比数据库，报告警察。 应用：
树莓派+摄像头、GPS、SD
Page2
实时性、可行性
实时性：GPS和路标映射
|  | 问题描述 |  | advantages | disadvantages
An Iteratively Optimized Patch Label Inference Network for Automatic Pavement Distress Detection | https://ieeexplore-ieee-org.ezproxy.lib.gla.ac.uk/document/9447759 | it is very challenging, since the pavement imaging suffers from uneven illumination, chromatic aberration, road markings in the background, and high diversity in the appearance of various distresses, such as cracks, potholes, erosive pits, and their mixtures | traditional pavement distress detection scheme |  | 1. mainly manual detection, which requires a large number of professionals and fruitful domain knowledge. 2.Moreover, professional testing requires expensive professional sensors
|  |  | Convolutional Neural Networks (CNNs) |  | CNN models often translate the image into a fixed low resolution image and then accomplish the classification based on the entire image. Such image translation will lose a lot of image information particularly for the high resolution images.
A New Road Damage Detection Baseline with Attention Learning | https://www.mdpi.com/2076-3417/12/15/7594 | As shown in Figure 1, multiple types of damage can appear in the same image. Although they do not overlap, the features of each kind of damage are very close to those of healthy road surfaces. In many cases, it is difficult even for the human eye to correctly classify only based on the images taken by vehicle cameras without field investigation.
|  | Due to various climates, road infrastructure standards and traffic rules, there are obvious differences in the data distributions of road damage among countries. |  | when road maintenance vehicles or driverless cars patrol daily in the future, they can provide timely feedback via uploading collected images to the cloud or server through 5G technology.
the ARDR algorithm can distinguish whether there is damage in the feedback images and give maintenance warnings for serious segments. This mode of ADRD can improve maintenance efficiency, reduce the economic cost caused by untimely maintenance and can reduce the number of traffic accidents caused by road damage.
Road defect detection from on-board cameras with scarce and cross-domain data | https://www.sciencedirect.com/science/article/pii/S0926580522004988
Road Damage Detection and Classification Using Deep Neural Networks with Smartphone Images | https://onlinelibrary-wiley-com.ezproxy.lib.gla.ac.uk/doi/full/10.1111/mice.12387

## Ins & YouTube脚本
照片 | 内容 | 备注
周一周会照片 | 文案：安排一周计划
周三实验课照片 | 问老师拍照
动手用器件拍照
讨论照片
团建照片
论文中间稿照片 |  | ♻️文字演讲稿
最终成果照片
视频/vlog | 内容 | 备注
周会vlog
解决困难视频 | 哪里困难，如何解决，如何克服 | 文字演讲稿可作为论文基础
有进展视频 |  | 文字演讲稿可作为论文基础
milestone视频 | 完成嵌入式，录一个介绍视频 | 文字演讲稿可作为论文基础
| 完成算法，录一个介绍视频 | 文字演讲稿可作为论文基础
最终成果视频
社交媒体发布内容侧重团队活动/工作还是项目本身？
youtube发布项目进展，ins发布一些团队活动